## Sheet1
S.No | Phase | Task | Details | Start Date | End Date | Assigned To | Status | Resource Needs | Hardware Involved | Software Involved | Tools Required | Testing Required | Documentation Needed | Peer Review Status | Testing Completed | Approved By Team | Submitted to GitHub | Final Review Status
1 | Project Initialization | Define project scope & objectives | Clarify Aqua Feed Pi's real-world problem, realtime necessity, and outcomes | 2025-02-01 | 2025-02-02 | All | Done | None | None | None | None | No | Yes | Done | Not Required | Yes | Submitted | Done
2 | Project Initialization | Submit final form on Moodle | Upload member list + GitHub link | 2025-02-02 | 2025-02-03 | Atharv & Gagan | Done | GitHub | None | None | None | No | Yes | Done | Not Required | Yes | Submitted | Done
3 | Project Initialization | GitHub repo setup | Create README, license, main branches, and placeholder files | 2025-02-04 | 2025-02-06 | Gagan & Syafiq | Done | GitHub | None | None | None | No | Yes | Done | Not Required | Yes | Submitted | Done
4 | Project Initialization | Pitch slides creation | Design 2 slides covering concept, hardware, realtime value | 2025-04-04 | 2025-04-05 | Gagan & Atharv | Done | Microsoft PPT | None | None | Microsoft PPT | No | Yes | Done | Not Required | Yes | Submitted | Done
5 | Project Initialization | Initial pitch delivery | Present project and receive feedback | 2025-02-05 | 2025-02-12 | All | Done | Microsoft PPT | None | None | Microsoft PPT | No | Yes | Done | Not Required | Yes | Submitted | Done
6 | Design & Planning | Define data flow diagram | Visualize the flow of sensor data to motor control and UI | 2025-02-06 | 2025-02-15 | Rahil & Syafiq | Done | Canva | None | Canva | Canva | No | Yes | Done | Not Required | Yes | Submitted | Done
7 | Design & Planning | Hardware specification | List and finalize required components (servo, sensors, Pi) | 2025-02-15 | 2025-02-25 | Wen Jun & Atharv | Done | None | None | None | None | No | Yes | Done | Not Required | Yes | Submitted | Done
8 | Design & Planning | Hardware procurement | Order parts using £45 budget and technician access | 2025-02-26 | 2025-03-03 | Wen Jun & Atharv | Done | None | None | None | None | No | Yes | Done | Not Required | Yes | Submitted | Done
9 | Design & Planning | Class design (UML-style) | Map out object-oriented structure using SOLID principles | 2025-03-05 | 2025-03-09 | Rahil & Wen Jun | Done | None | None | None | None | No | Yes | Done | Not Required | Yes | Submitted | Done
10 | Design & Planning | Create pin mapping and wiring plan | Document GPIO pin usage and safety checks | 2025-03-03 | 2025-03-04 | Rahil & Syafiq | Done | None | None | None | None | No | Yes | Done | Not Required | Yes | Submitted | Done
11 | Development Phase 1 | 3D Design of the components | Create a 3D model in Sketch up | 2025-02-16 | 2025-02-26 | Gagan & Syafiq | Done | Sketchup | None | Sketchup | Sketchup | No | Yes | Done | Not Required | Yes | Submitted | Done
12 | Development Phase 1 | 3D Printing of the components | 3D printing of the model in the University Lab | 2025-03-05 | 2025-03-08 | Gagan & Syafiq | Done | Sketchup | None | Sketchup | Sketchup | No | Yes | Done | Not Required | Yes | Submitted | Done
13 | Development Phase 1 | Sensor integration | Interface temp and water level sensors to Pi, validate data readout | 2025-03-09 | 2025-03-12 | Rahil & Atharv | Done | Rasaspberry Pi | Rasaspberry Pi | C++ | Rasaspberry Pi, C++ | Yes | Yes | Done | Done | Yes | Submitted | Done
14 | Development Phase 1 | Motor control setup | Use PWM via GPIO to control servo for feeding | 2025-03-10 | 2025-03-15 | Wen Jun & Atharv | Done | Servo Motor, Rasaspberry Pi | Servo Motor, Rasaspberry Pi | C++ | Servo Motor, Rasaspberry Pi, C++ | Yes | Yes | Done | Done | Yes | Submitted | Done
15 | Development Phase 1 | UI control setup | Basic GUI or command interface for feed timing/parameters | 2025-03-13 | 2025-03-16 | Rahil & Atharv | Done | Rasaspberry Pi | Rasaspberry Pi | C++ | Rasaspberry Pi, C++ | Yes | Yes | Done | Done | Yes | Submitted | Done
16 | Development Phase 1 | Callback/event framework | Implement threaded or signal-driven logic for events | 2025-03-16 | 2025-03-19 | Rahil | Done | C++ | None | C++ | C++ | Yes | Yes | Done | Done | Yes | Submitted | Done
17 | Development Phase 1 | Latency & fault handling | Test & optimize sensor-to-response latency, handle anomalies | 2025-03-19 | 2025-03-24 | Rahil | Done | Rasaspberry Pi | Rasaspberry Pi | C++ | Rasaspberry Pi, C++ | Yes | Yes | Done | Done | Yes | Submitted | Done
18 | Development Phase 1 | Sensor calibration | Calibrate temperature and water level sensors for accuracy | 2025-03-19 | 2025-03-20 | Atharv & Rahil | Done | Rasaspberry Pi, Sensors | Rasaspberry Pi, Sensors | C++ | Rasaspberry Pi, Sensors,C++ | Yes | Yes | Done | Done | Yes | Submitted | Done
19 | Development Phase 2 | Create sensor abstraction class | Design modular class for sensor readouts | 2025-03-18 | 2025-03-19 | Rahil | Done | C++ | None | C++ | C++ | Yes | Yes | Done | Done | Yes | Submitted | Done
20 | Development Phase 2 | Basic signal plotting | Plot real-time signals on screen or log to file | 2025-03-19 | 2025-03-20 | Gagan & Wen Jun | Done | C++ | None | C++ | C++ | Yes | Yes | Done | Done | Yes | Submitted | Done
21 | Development Phase 2 | Implement alert system | Notify if thresholds are crossed (e.g., low water) | 2025-03-20 | 2025-03-21 | Rahil & Wen Jun | Done | C++ | None | C++ | C++ | Yes | Yes | Done | Done | Yes | Submitted | Done
22 | Development Phase 2 | UI event binding | Bind UI controls to logic and backend state | 2025-03-21 | 2025-03-22 | Rahil | Done | C++ | None | C++ | C++ | Yes | Yes | Done | Done | Yes | Submitted | Done
23 | Development Phase 2 | Non-blocking threading | Use threads/signals to avoid blocking in loops | 2025-03-21 | 2025-03-23 | Rahil & Wen Jun | Done | C++ | None | C++ | C++ | Yes | Yes | Done | Done | Yes | Submitted | Done
24 | Development Phase 2 | Exception handling routines | Add safety checks and exception logging | 2025-03-23 | 2025-03-25 | Rahil & Wen Jun | Done | C++ | None | C++ | C++ | Yes | Yes | Done | Done | Yes | Submitted | Done
25 | Development Phase 2 | Webpage for User Interface | Creating webpage and integrate UI with backend | 2025-03-26 | 2025-03-28 | Gagan & Syafiq | Done | C++, JSON, Github | Raspberry Pi, Sensors, Motor | C++, JSON, Github | C++, JSON, Github | Yes | Yes | Done | Done | Yes | Submitted | Done
26 | Development Phase 2 | Create user features | Debugging backend to integrate with UI, add user features (e.g., pH level plot) | 2025-03-27 | 2025-03-29 | Gagan & Syafiq | Done | C++, JSON, Github | Raspberry Pi, Sensors, Motor | C++, JSON, Github | C++, JSON, Github | Yes | Yes | Done | Done | Yes | Submitted | Done
27 | Testing & Version Control | Set up Git strategy | Define commit discipline, use branches & issues | 2025-04-24 | 2025-04-24 | Rahil & Wen Jun | Done | C++ | None | C++ | C++ | No | Yes | Done | Not Required | Yes | Submitted | Done
28 | Testing & Version Control | Unit & integration testing | Test each module independently + integrated run | 2025-04-25 | 2025-04-26 | Rahil & Wen Jun | Done | AquaFeeder, Rasaspberry Pi | AquaFeeder, Rasaspberry Pi | C++ | AquaFeeder, Rasaspberry Pi, C++ | Yes | Yes | Done | Done | Yes | Submitted | Done
29 | Testing & Version Control | Create test cases for each module | Unit test for sensor, feeder, and UI modules | 2025-03-28 | 2025-03-30 | Atharv & Rahil | Done | AquaFeeder, Rasaspberry Pi | AquaFeeder, Rasaspberry Pi | C++ | AquaFeeder, Rasaspberry Pi, C++ | Yes | Yes | Done | Done | Yes | Submitted | Done
30 | Testing & Version Control | Run latency tests | Measure sensor-to-actuation time under load | 2025-03-28 | 2025-03-30 | Rahil & Wen Jun | Done | C++ | C++ | C++ | C++ | Yes | Yes | Done | Done | Yes | Submitted | Done
31 | Documentation & PR | Write GitHub documentation | README, usage, diagrams, architecture, hardware setup | 2025-03-26 | 2025-03-28 | Gagan & Syafiq | Done | GitHub | None | None | GitHub | No | Yes | Done | Not Required | Yes | Submitted | Done
32 | Documentation & PR | Create visual content | Demo, record GIF, upload to repo | 2025-03-25 | 2025-03-27 | Gagan & Syafiq | Done | Camera | None | None | Camera | No | Yes | Done | Not Required | Yes | Submitted | Done
33 | Documentation & PR | Social media & promotion | Announce project on LinkedIn & Instagram | 2025-03-02 | 2025-03-03 | Atharv & Gagan | Done | Instagram & LinkedIn | None | None | Instagram & LinkedIn | No | Yes | Done | Not Required | Yes | Submitted | Done
34 | Finalization | Create GitHub release | Package, tag, and publish final release | 2025-04-04 | 2025-04-10 | All | Done | GitHub | None | None | GitHub | No | Yes | Done | Not Required | Yes | Submitted | Done
35 | Finalization | Freeze codebase | Stop feature development, perform code cleanup and bug fixing | 2025-04-12 | 2025-04-15 | Atharv & Wen Jun | Done | C++ | None | None | C++ | Yes | Yes | Done | Done | Yes | Submitted | Done
36 | Finalization | Final testing | Comprehensive system testing and final bug resolution | 2025-04-13 | 2025-04-17 | Gagan & Wen Jun | Done | AquaMatic | AquaMatic | C++ | AquaMatic, C++ | Yes | Yes | Done | Done | Yes | Submitted | Done
37 | Finalization | Prepare final GitHub release | Create and tag a stable release on GitHub | 2025-04-17 | 2025-04-18 | Rahil & Wen Jun | Done | GitHub | None | None | GitHub | No | Yes | Done | Not Required | Yes | Submitted | Done
38 | Finalization | Update final documentation | Finalize README, diagrams, and how-to sections | 2025-04-17 | 2025-04-18 | Gagan & Wen Jun | Done | GitHub | None | None | GitHub | No | Yes | Done | Not Required | Yes | Submitted | Done
39 | Finalization | Upload video demo | Create, edit, and upload a walkthrough demo | 2025-04-17 | 2025-04-19 | Atharv & Gagan | Done | GitHub | None | None | GitHub | No | Yes | Done | Not Required | Yes | Submitted | Done
40 | Finalization | Peer review & internal feedback | Review by all team members and adjustments based on feedback | 2025-04-18 | 2025-04-20 | All | Done | GitHub | None | None | GitHub | No | Yes | Done | Not Required | Yes | Submitted | Done
41 | Finalization | Submit final GitHub link to Moodle | Official submission of final deliverables | 2025-04-20 | 2025-04-21 | All | Done | GitHub | None | None | GitHub | No | Yes | Done | Not Required | Yes | Submitted | Done
42 | Finalization | Backup & archive | Save a copy of code, documentation, and assets | 2025-04-20 | 2025-04-21 | All | Done | None | None | None | None | No | Yes | Done | Not Required | Yes | Submitted | Done
43 | Finalization | Team retrospective | Discuss project outcomes, lessons learned, improvements | 2025-04-21 | 2025-04-23 | All | Pending | None | None | None | None | No | Yes | Done | Not Required | Yes | Submitted | Done